}

Guide 1. APT Project Definition

Capstone Course

- PART I

1. Personal Background

Below is a table in which you must complete the requested information.

| Student Name | - Gabriela Barraza Viveros - Camila Rumino Román - Daniel Santelices Muñoz |
| --- | --- |
| National ID (RUT) | - 17.103.188-5 - 20.004.500-9 - 18.839.969-K |
| Degree Program / Major | Computer Engineering |
| Campus | Puente Alto |

2. APT Project Description

In the description, you must briefly state the name of your APT project and the graduate profile competencies you will put into practice. If performance areas are defined in your degree program, also mention which performance areas the project is linked to.

| Project Name | VAYO |
| --- | --- |
| Performance Area(s) | Software development, mobile application development, databases, UX/UI Design design, and quality assurance. |
| Competencies | - Requirements elicitation and analysis. - Design and development of software solutions. - Mobile application development. - Database development and management. - Services and API integration. - Software quality assurance and control. - IT project management and documentation. |

3. APT Project Rationale

Below are different fields you must complete with the requested information. This section aims for you to describe your project in detail and justify its relevance and pertinence.

| Relevance of the APT Project | Currently, when a person organizes a trip, they must use different applications and platforms to search for accommodations, restaurants, activities, transportation, points of interest, and maps. In addition, they need to manage schedules, reservations, budgets, and expenses. Because this information is scattered across different places, it can be difficult to maintain an organized plan and quickly access all necessary information during the trip. This project seeks to address this situation through a mobile application that allows trip-related information to be centralized in a single place. The solution is primarily oriented toward travelers who need to plan and manage their trips in an organized way, especially when they are in locations where they may have limited or no Internet connectivity. The project is relevant to the professional field of Computer Engineering, as it involves applying knowledge of software development, databases, user interface design, external services integration, and quality assurance testing. The value contribution consists of delivering a tool that streamlines trip organization and allows users to access important information quickly and in an organized manner. |
| --- | --- |
| APT Project Description | The project consists of developing a mobile application designed to facilitate travel planning and management, enabling travelers to centralize all necessary information in one single place. When planning a trip, it is common to use multiple applications to find places, restaurants, accommodations, activities, maps, and track expenses. This causes information to be scattered and disorganized. Furthermore, many of these apps require a constant Internet connection, which makes them difficult to use during a trip when mobile data or cellular signal is unavailable. Furthermore, it will feature local storage functionality using Offline-First SQLite, allowing users to query and manage previously stored information when the device has no Internet connection. When connectivity is restored, data can be synchronized with cloud services via Supabase BaaS. From this problem arises the need for a solution that centralizes the core tools of a trip in one place. VAYO will allow travelers to organize itineraries by days and schedules, save places of interest, log activities, manage budgets and expenses, and view locations on interactive maps. It will also feature offline functionality to access stored information without an internet connection and incorporate artificial intelligence as an aid for organizing activities. |
| Relevance of the Project to the Graduate Profile | The project aligns directly with the Computer Engineering graduate profile, as it requires applying skills and knowledge related to problem analysis, software development, technological solution design, and IT project management. Developing the application requires analyzing user needs, defining requirements, architecting the solution, developing core features, integrating diverse third-party technological services, and conducting tests to verify optimal performance. Software development competencies will enable building the mobile application and its features, while problem-solving and systems analysis competencies will transform the identified problem into a viable technological solution. Project management skills will also be essential to organize team tasks, deadlines, and responsibilities. |
| Alignment with Professional Interests | The project aligns with the professional interests of the team members, as it allows applying various areas of Computer Engineering, primarily software development, mobile application engineering, UX/UI Design design, databases, services integration, and quality assurance. Furthermore, the project allows each team member to contribute from their area of strength and deepen their technical expertise through collaborative teamwork. Throughout its development, we will apply knowledge gained across our degree and gain practical experience in an end-to-end engineering project, from analysis and design to development, testing, and deployment. |
| Feasibility of Developing the APT Project | The project is highly feasible due to a well-defined academic timeline and established scope, enabling gradual activity scheduling throughout the semester. Work will be divided into structured phases: planning, analysis and design, development, testing, and deployment. Developing the project requires development workstations, software development tools, Figma for interface design, Git repositories for version control, React Native, SQLite, and external APIs for maps, places, and artificial intelligence. Facilitating factors include clear division of roles and responsibilities among team members, leverage of proven modern frameworks, and continuous testing throughout the development lifecycle. Among the main difficulties, potential integration issues with external services, development bugs, or time constraints could arise. To mitigate these risks, activities will be closely monitored, core functionalities will be prioritized, and periodic testing will be conducted throughout development. |

- PART II

4. Objectives

In this section, you must define the general and specific objectives of the APT Project. Objectives must be stated clearly, concisely, and self-explanatorily. It is suggested to draft them using an infinitive verb to specify concrete actions.

| General Objective | Develop a mobile application that centralizes and streamlines trip planning and management, integrating itineraries, activities, accommodations, transportation, maps, expenses, and artificial intelligence, with offline data availability and cloud synchronization. |
| --- | --- |
| Specific Objectives | - Design an intuitive mobile application that allows creating and managing trips. - Implement an itinerary planning system organized by calendar and schedules. - Implement an itinerary planning system organized by calendar and time slots. - Implement a module to record and categorize trip expenses. - Incorporate interactive maps to visualize planned locations and traveled routes. - Consolidate information related to accommodations, restaurants, activities, transportation, and points of interest. - Implement a module to track and categorize trip expenses. - Implement synchronization with cloud services to keep user information updated. |

Consolidate travel information regarding accommodations, restaurants, activities, transportation, and points of interest.

In the following section, you must describe the methodology, specific to your discipline, that you will use to execute the APT project described above, including work phases and methods.

Methodology Description

For the development of the VAYO project, we will use a traditional engineering methodology, as it allows organizing the project in a structured manner and following a sequence of predefined phases. The methodology encompasses distinct phases. First, requirements elicitation and definition will identify core user needs and functional requirements. Next, in the analysis and design phase, we will specify use cases, UI mockups, software architecture, relational data models, and technical documentation. Subsequently, in the development phase, all features will be implemented using React Native, Supabase BaaS, and Offline-First SQLite, alongside third-party API integrations including Google Maps, Google Places, and Google Gemini. Following development, comprehensive testing will verify system functionality and validate compliance with all defined requirements. Any defects identified will be resolved prior to the final delivery. Finally, deployment and project closure will encompass final build packaging, documentation, user manuals, scope verification, and final presentation.

6. Evidence / Deliverables

Below, describe what evidence and deliverables will be evaluated in the progress report and final report of your APT project. This evidence must be agreed upon with your instructor. Evidence refers to products developed during the project whose purpose is to demonstrate or document how the work has been implemented.

| Evidence Type (Progress or Final) | Evidence / Deliverable Name | Description | Justification |
| --- | --- | --- | --- |
| Progress | APT Project Definition | Document defining the project, problem statement, objectives, and scope. | Establish foundational parameters of the project to be built. |
| Progress | Project Charter | Document establishing project scope, objectives, team roles, and general conditions. | Formally define project boundaries, roles, and commitments. |
| Progress | Requirements Specification Sheet | Matrix of functional and non-functional requirements. | Define features, behavioral constraints, and system specifications. |
| Progress | SRS Report (Software Requirements Specification) | Formal software requirements specification and proposed technical solution. | Document the proposed architectural solution and functional attributes. |
| Progress | Gantt Chart | Project schedule and timeline. | Organize and track scheduled tasks, milestones, and deadlines. |
| Progress | Extended Use Cases Document | Document detailing interactions between users, systems, and error scenarios. | Formally specify user actions, business rules, and system responses. |
| Progress | UI Mockups | Graphical description of the project, showcasing the main views and screens of the application. | Establish visual interface layouts before technical development. |
| Progress | Software Architecture Document (SAD) | Document describing system architecture, layers, and technological components. system. | Define structural organization, data flows, and layer decoupling. |
| Progress | TO-BE Business Process Model | BPMN diagram representing optimized travel planning workflow. | Visualize business process improvements enabled by the app. |
| Progress | Data Dictionary | Document defining the terminology and terms used in the project development. | Facilitate the understanding of the information and data used by the system. |
| Progress | APT Project Development | Implementation artifacts demonstrating codebase progress. | Demonstrate steady progress in software construction. |
| Progress | Database Model | Entity-relationship model and relational database schema. | Define the data structure that will be used by the system. |
| Final | Mobile Application | Functional mobile build with implemented core features. | Demonstrate final deployed deliverable and operational software. |
| Final | Test Plan | Specification of test cases, test suites, and validation outcomes. | Verify software quality, data consistency, and defect resolution. |
| Final | Change Control Matrix | Formal registry tracking scope modifications and change requests. | Maintain traceability over requirements adjustments. |
| Final | Scope Verification | Audit document verifying compliance of delivered features against scope. | Validate that all planned deliverables satisfy original agreements. |
| Final | User Manual | End-user guide explaining how to navigate and use application features. | Provide instructions and guidance for travelers using the app. |
| Final | Project Closure Report | Final report summarizing project outcomes, lessons learned, and metrics. | Formally conclude project lifecycle and evaluate deliverables. |
| Final | APT Presentation Document | Slide deck prepared for final project defense before the evaluation committee. | Present engineering design, implementation highlights, and results. |

7. Work Plan

In the following table, define the planning of your APT Project according to requirements.

| APT Project Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Competency or Units of Competency | Activity / Task Name | Description Activityes/Tareas | Resources | Activity Duration | Person Responsible | Notes / Observations |
| APT Project | Project Definition | Define problem statement, solution concept, objectives, and project scope. | Computer, documentation | 10/08/2026 to 13/08/2026 | Entire team | Establishes project foundations. |
| Project Management | Project Charter | Draft and develop the Project Charter. | Computer, documentation | 14/08/2026 to 19/08/2026 | Entire team | Formally defines project scope and commitments. |
| Project Management | Team Organization | Define roles, team responsibilities, and task distribution. | Computer, documentation | 20/08/2026 to 21/08/2026 | Entire team | Organizes collaborative team workflows. |
| Project Management | Gantt Chart | Prepare overall project timeline. | Excel, computer | 24/08/2026 to 27/08/2026 | Camila | Schedules milestones and work packages. |
| Analysis | Requirements Definition | Identify and document functional and non-functional requirements. | Computer, documentation | 28/08/2026 to 03/09/2026 | Entire team | Defines application capabilities and constraints. |
| Analysis | Use Cases | Model interactions between users and the system. | Draw.io / UML modeling tool | 04/09/2026 to 08/09/2026 | Gabriela and Camila | Allows representing and modeling key system functionalities. |
| UX/UI Design | Mockup Design | Design the main user interfaces and navigation flow. | Figma | 09/09/2026 to 15/09/2026 | Gabriela | Defines visual aesthetics and user experience. |
| Architecture | SAD Architecture Document | Define the technological architecture of the solution. | Computer, documentation | 16/09/2026 to 21/09/2026 | Daniel | React Native, Supabase, and SQLite will be used. |
| Business Process | TO-BE Process | Design the improved business process enabled by the application. | Bizagi / documentation | 22/09/2026 to 25/09/2026 | Entire team | Represents the business process with the implemented solution. |
| Database Engineering | Data Modeling | Design relational schema, entity relationships, and constraints. | Supabase, SQLite | 26/09/2026 to 28/09/2026 | Daniel | Defines normalized storage architecture. |
| Software Development | Project Setup & Environment | Configure the development environment and source repository. | React Native, Expo, VS Code, Git | 29/09/2026 to 01/10/2026 | Daniel | Prepares scalable development environment. |
| Software Development | Database Engineering and Local Storage | Implement Supabase cloud backend and SQLite local-first engine. | Supabase, SQLite | 02/10/2026 to 07/10/2026 | Daniel | Enables seamless online and offline operations. |
| Software Development | User Management & Auth | Implement user registration, session handling, and login. | Supabase Auth, React Native | 08/10/2026 to 13/10/2026 | Daniel | Includes email/password and OAuth authentication. |
| Software Development | Trips & Daily Itineraries | Implement creation and management of trips and itineraries. | React Native, Supabase, SQLite | 14/10/2026 to 21/10/2026 | Daniel | Core business module of the platform. |
| Software Development | Places, Activities & Transport | Implement management of places, activities, and transportation. | React Native, Google Places | 22/10/2026 to 28/10/2026 | Daniel | Integrates external location services. |
| Software Development | Maps & Geolocation | Implement maps, geolocation, and place visualization. | Google Maps, Expo Location | 29/10/2026 to 02/11/2026 | Daniel | Provides rich interactive geospatial views. |
| Software Development | Budget & Expenses | Implement budget, categories, and expense tracking. | React Native, Supabase, SQLite | 03/11/2026 to 07/11/2026 | Daniel | Includes automatic currency conversion. |
| Software Development | Travel Log & Documents | Implement photos, travel log, and trip documents. | React Native, Supabase Storage | 08/11/2026 to 10/11/2026 | Gabriela and Daniel | Allows storing trip memories, tickets, and travel documents. |
| Software Development | Local Notifications | Implement schedule-based reminders and local native alarms. | Expo Notifications | 11/11/2026 to 15/11/2026 | Daniel | Functions independently of network connectivity. |
| Software Development | Artificial Intelligence | Integrate generation of itinerary suggestions. | Google Gemini API | 13/11/2026 to 15/11/2026 | Daniel | Will generate recommendations based on user needs. |
| Quality Assurance | Test Plan | Define test specifications, test suites, and acceptance criteria. | Documentation, computer | 16/11/2026 to 18/11/2026 | Gabriela and Camila | Establishes quality verification standards. |
| Quality Assurance | Functional Testing | Verify the operation and functionality of developed modules. | Application build, test matrix | 19/11/2026 to 23/11/2026 | Gabriela and Camila | Tracks and logs resolved anomalies. |
| Quality Assurance | Usability Testing | Evaluate interface accessibility, responsiveness, and user satisfaction. | Prototype / app build, test users | 24/11/2026 to 29/11/2026 | Gabriela and Camila | Assesses usability heuristics and user flows. |
| Deployment | Final Build Packaging | Generate and prepare the final build of the application. | Expo, Android, computador | 30/11/2026 to 01/12/2026 | Daniel | Prepares release artifacts for project defense. |
| Documentation | User Manual | Draft documentation and user instructions for the application. | Computer, application build | 02/12/2026 to 03/12/2026 | Gabriela | Explains application features and navigation. |
| Project Management | Project Closure | Prepare project closure documentation and verify scope fulfillment. | Documentation | 04/12/2026 to 05/12/2026 | Entire team | Audits fulfillment of project objectives. |
| APT Project | Final Defense Presentation | Prepare slide deck and present APT project to evaluation committee. | PowerPoint, running application demo | 07/12/2026 | Entire team | Final Defense Presentation of the project. |

8. Gantt Chart

Find a Gantt Chart format that suits you and organize within it the activities planned in the previous section, considering the period assigned for the development of your APT Project. You must maintain the academic period timeline across the three phases established by the Capstone Course.

| Activity | Phase 1 |  |  |  | Phase 2 |  |  |  |  |  |  |  |  |  |  |  | Phase 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W 1 | W 2 | W 3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14 | W 15 | W 16 |  | W 17 | W 18 |
| APT Project Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Charter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Requirements Specification Sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SRS Report (Software Requirements Specification) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gantt Chart |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Extended Use Case |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UI Mockups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Software Architecture Document (SAD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TO-BE Business Process Model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Dictionary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| APT Project Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobile Application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Change Control Matrix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scope Verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Closure Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| APT Presentation Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If the APT Project is group-based, indicate the name of the person responsible for each task or activity in this column. This will subsequently allow differentiating the evaluation for each team member.